## Neha
Connector Name | Status | Priority | R& D Status | R& D ETA | Design Document | Smart Connector Document | Design ETA | Design Status | Dev ETA | Completed | Unit Testing ETA | Unit Testing Status | Versioning | Push to Testing Team | Comments
Looker |  | 3 | Completed |  | Not yet started | Completed |  | Completed |  | Completed |  | In Progress | Yet to start | Completed | Working on the issues addressed by testting team. Nw The issues are fixed for instance below10.x Nawaz is working on design document.
Talend FWD |  | 8 | Completed |  | Not yet started | Completed |  | Completed |  | Completed |  | Completed | Yet to start | Yet to start | The connector hasn't been tested by testing team yet
DS_Talend Plugin Connector |  | 1 | Completed |  | Not yet started | Completed |  | Completed |  | Partially Completed | 2021-09-02 | Yet to start | Yet to start | Yet to start | Few pieces in the connector are pending
IDQ |  | 1 | Completed |  | Not yet started | Not yet started |  | Not yet started |  | In progress | 2021-09-02 | Yet to start | Yet to start | Yet to start | Mapping specification completed with extended properties-- this status for one mapping, need to validate code for all the mappings working on lineage fixes
INFA TO SQL |  | 7 | In progress | 2021-09-02 | Not yet started | Not yet started |  | Not yet started |  | Not yet started |  | Yet to start | Yet to start | Yet to start
Informatica Reverse for USCC |  | 4 | Not yet started |  | Not yet started | Not yet started |  | Not yet started |  | Not yet started |  | Yet to start | Yet to start | Yet to start
BODS Reverse Connector |  | 2 | Completed |  | Not yet started | Not yet started |  | Completed |  | Completed |  | Yet to start | Yet to start | Yet to start | To enexis 2-3-4 component mappings are delievered, work is in progress
SNAPLOGIC |  | 6 | In progress |  | Not yet started | Not yet started |  | Completed | 2021-09-02 | In progress |  | Yet to start | Yet to start | Yet to start | Sreekanth is working on this piece
Informatica BDM forward |  | 9 | In progress |  | Not yet started | Not yet started |  | Not yet started |  | Not yet started |  | Yet to start | Yet to start | Yet to start | Working on BDM installation with Vijay Shared BDM mapping with client for validation, waiting for their analysis

## Nawaz
Connector Name | Status | Priority | R& D Status | R& D ETA | Design Document | Smart Connector Document | Design ETA | Design Status | Dev ETA | Dev Status | Unit Testing ETA | Unit Testing Status | Versioning | Push to Testing Team | Comments
Cognos Export Utilities | Completed | 9 | Completed |  | Pending | Completed |  | Completed |  | Completed |  | Completed | Pending | Not Yet Done | Already running in Customer Env. Working on Enhancement and Maintenance
EDF Talend ETL Reverse Connector | Completed | 4 | Completed |  | Pending | Pending |  | Completed |  | Completed |  | Pending | Pending | Not Yet Done | Need to fix mapping names
OWB TO INFA | Not Started | 5 | NA |  | NA | NA |  | NA |  | NA |  | NA | NA | NA | NA
OWB Reverse | Started | 1 | Just Initiated | 2021-12-02 | [10 empty] | Ran Talend Job, needed to crossverify with Sreekanth once before running in EMM
OWB_INFA Plugin Connector | Not Started | 3 | NA |  | NA | NA |  | NA |  | NA |  | NA | NA | NA | NA
ORACLE SQL Reverse for EON | Completed | 7 | Completed |  | Pending | Completed |  | Completed |  | Completed |  | Completed | Completed | Not Yet Done | Already running in Customer Env. Working on Enhancement and Maintenance
ORACLE SQL Export for EON | Completed | 6 | Completed |  | Pending | Completed |  | Completed |  | Completed |  | Completed | Completed | Not Yet Done | Already running in Customer Env. Working on Enhancement and Maintenance
BTEQ Reverse CMS | Completed | 8 | Completed |  | Pending | Completed |  | Completed |  | Completed |  | Completed | Completed | Done | Updated Package Zip needs to be sent to customer
Matillion Auto Import | Not Started | 2 | Just Initiated
SAPBO WAR | In Progress |  | In Progress |  | NA | NA |  | NA |  | In Progress |  | NA | NA | NA | Awaiting Updated WAR from pradeep

## Sabiya
Connector Name | Status | Priority | R& D Status | R& D ETA | Design Document | Smart Connector Document | Design ETA | Design Status | Dev ETA | Dev Status | Unit Testing ETA | Unit Testing Status | Versioning | Push to Testing Team | Comments
ODI REVERSE |  | 1 | inprogress | [11 empty] | working on column Lineage
INFA TO TALEND PLUGIN Connector |  | 2 | in progress | [11 empty] | working on component lineage
AWS Glue |  | 3 | in progress
INFA Reverse |  | 4

## Manisha
Connector Name | Status | Priority | R& D Status | R& D ETA | Design Document | Smart Connector Document | Design ETA | Design Status | Dev ETA | Dev Status | Unit Testing ETA | Unit Testing Status | Versioning | Push to Testing Team | Comments
Stratification Connector | Completed | 4 |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | In Progress | In Progress
Informatica Forward | Pending | 6
ORACLE TO SQL ( SNOWFLAKE ) Mig Connector | In Progress | 2
BODS TO Matillian Plugin Connector | In Progress | 1 | In Progress |  | Not Started | Not Started |  |  |  | In Progress
Matillian FWD Connector | In Progress | 3 | In Progress | [11 empty] | From Simple 2 and 3 components are completed and prepared the connector...and Matillion Auto Import done through java code
AWS Glue API Analysis | Not Started | 5 | Not Started |  | Not Started | Not Started |  | Not Started |  | Not Started |  | Not Started
SQL Reverse | Not Started | 7 | Not Started |  | Not Started | Not Started |  | Not Started |  | Not Started |  | Not Started
Standard Informatica Forward Enhancement | Not Started |  | Not Started |  | Not Started | Not Started |  | Not Started |  | Not Started |  | Not Started
ETL Migration Configuration | Not Started |  | Not Started |  | Not Started | Not Started |  | Not Started |  | Not Started |  | Not Started
Note : Status - Completed - Everything should be complete.
In-Progress - Some of Steps are In-Progress.
In Design Phase
In Analysis Phase
R & D Phase

## Abdul
Connector Name | Status | Priority | R& D Status | R& D ETA | Design Document | Smart Connector Document | Design ETA | Design Status | Dev ETA | Dev Status | Unit Testing ETA | Unit Testing Status | Versioning | Push to Testing Team | Comments
DS Reverse HP | Completed | 1 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Yet Done | Already running in Customer Env. Working on Enhancement and Maintenance. Need to verify few enhancement in Customer env.
SQL Reverse HP | Completed | 1 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Yet Done | Already running in Customer Env. Working on Enhancement and Maintenance
CIGNA Connector ( erwin Data Modeling Reverse Connector) |  | 5
INFA Reverse CMS | Completed | 2 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Yet Done | Already running in Customer Env. Working on Enhancement and Maintenance
BTEQ Reverse CMS | Completed | 2 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Yet Done | Already running in Customer Env. Working on Enhancement and Maintenance
COGNOS Reverse CMS | Completed | 2 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Yet Done | Already running in Customer Env. Working on Enhancement and Maintenance
SAP BO CMS | Completed | 2 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Not Yet Done | Already running in Customer Env. Working on Enhancement and Maintenance
AWS Glue | In - Progress | 3 | In - Progress | [11 empty] | Created AWS Glue Mapping in AWS Cloud portal. Currently working with Sabiya for Talend Code to replicate the same in Talend.
Alteryx | In - Progress | 4 | In - Progress
Informatica AUTO EXPORT EON | Partially Completed | 6 | [12 empty] | Customer need to come back.
Informatica REVERSE EON | Partially Completed | 7 | [12 empty] | Customer need to come back.
IICS REVERSE | In - Progress | 8 | [12 empty] | Able to extract Information via Postman API from IICS.
IICS AUTO EXPORT |  | 9
Oracle to PostgreSQL | In - Progress | 3 | Completed | Completed | Pending | Pending | Pending | Pending | Pending | In-Progress | Pending | Pending | Pending | Pending | Oracle to PostgreSQL , View Compilation Completed. Working on Function and Procedure. Prepare property files for all the function ( Ora to Post ) , DataTypes .